## Gantt Chart (daily)
FitForm AI - Project Gantt Chart (daily), IMP Part B
Steve Flinston (24123119) ¦ 6FTC2062 Individual Major Project ¦ Supervisor: Wong Kim Siong ¦ Updated 31 Oct 2026 (after Session 3)
 | time axis 2026-09-14 to 2026-12-02
Task Name | Outline week | Start | End | Days | Status | 2026-09-14: September 2026; 2026-10-01: October 2026; 2026-11-01: November 2026; 2026-12-01: Dec
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
[6 empty] | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2
[6 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W |  |  | Start date | End date
1. Set up Python 3.11 virtual environment (Raspberry Pi OS + laptop) | W1 | 14 Sep | 2 Oct | 19 | Done | [80 empty] | Heading |  | 2026-09-14 | 2026-10-02
Install Raspberry Pi OS on the microSD card; first boot of the Pi 5 |  | 14 Sep | 16 Sep | 3 | Done | [80 empty] | Task |  | 2026-09-14 | 2026-09-16
Laptop Python environment; fix library version error |  | 14 Sep | 18 Sep | 5 | Done | [80 empty] | Task |  | 2026-09-14 | 2026-09-18
Pi 5 Python 3.12 virtual environment with uv (OS ships Python 3.13) |  | 28 Sep | 2 Oct | 5 | Done | [80 empty] | Task |  | 2026-09-28 | 2026-10-02
2. Install and configure OpenCV | W2 | 16 Sep | 2 Oct | 17 | Done | [80 empty] | Heading |  | 2026-09-16 | 2026-10-02
Install OpenCV 4.11 on the laptop; test the webcam |  | 16 Sep | 18 Sep | 3 | Done | [80 empty] | Task |  | 2026-09-16 | 2026-09-18
Install OpenCV on the Pi 5; remove conflicting builds |  | 30 Sep | 2 Oct | 3 | Done | [80 empty] | Task |  | 2026-09-30 | 2026-10-02
3. Install and configure MediaPipe; test camera feed and GPIO wiring for LED/buzzer | W3 | 17 Sep | 4 Nov | 49 | In progress | [80 empty] | Heading |  | 2026-09-17 | 2026-11-04
Install MediaPipe on the laptop; test pose on the webcam |  | 17 Sep | 19 Sep | 3 | Done | [80 empty] | Task |  | 2026-09-17 | 2026-09-19
Install MediaPipe 0.10.18 on the Pi 5; run the logic tests |  | 1 Oct | 3 Oct | 3 | Done | [80 empty] | Task |  | 2026-10-01 | 2026-10-03
Pi camera support (rpicam) and AI Camera firmware |  | 3 Oct | 7 Oct | 5 | Done | [80 empty] | Task |  | 2026-10-03 | 2026-10-07
GPIO wiring test of the LEDs and buzzer on the breadboard (moved) |  | 2 Nov | 4 Nov | 3 | Not started | [80 empty] | Task |  | 2026-11-02 | 2026-11-04
4. Develop MediaPipe Pose landmark extraction (shoulder, elbow, wrist, hip coordinates) | W4 | 19 Sep | 7 Oct | 19 | Done | [80 empty] | Heading |  | 2026-09-19 | 2026-10-07
Restructure the prototype into modules (pose_engine.py) |  | 19 Sep | 25 Sep | 7 | Done | [80 empty] | Task |  | 2026-09-19 | 2026-09-25
Use MediaPipe 3D world landmarks (view-independent) |  | 5 Oct | 7 Oct | 3 | Done | [80 empty] | Task |  | 2026-10-05 | 2026-10-07
5. Implement joint-angle calculation functions (elbow, torso, wrist angles) | W5 | 5 Oct | 8 Oct | 4 | Done | [80 empty] | Heading |  | 2026-10-05 | 2026-10-08
Elbow angle and upper-arm drift check (replaces hip swing check) |  | 5 Oct | 7 Oct | 3 | Done | [80 empty] | Task |  | 2026-10-05 | 2026-10-07
Wrist angle from the hand knuckles (MediaPipe Hands) |  | 7 Oct | 8 Oct | 2 | Done | [80 empty] | Task |  | 2026-10-07 | 2026-10-08
6. Build the bicep curl rep-counting state machine with form-validation checks | W6 | 21 Sep | 27 Oct | 37 | Done | [80 empty] | Heading |  | 2026-09-21 | 2026-10-27
State machine for left and right arms (laptop test) |  | 21 Sep | 26 Sep | 6 | Done | [80 empty] | Task |  | 2026-09-21 | 2026-09-26
Clenched-fist check with MediaPipe Hands |  | 6 Oct | 8 Oct | 3 | Done | [80 empty] | Task |  | 2026-10-06 | 2026-10-08
Fix live rep counting on the Pi using the debug view |  | 8 Oct | 22 Oct | 15 | Done | [80 empty] | Task |  | 2026-10-08 | 2026-10-22
Fist direction: per-arm calibration from labelled runs; tip instead of reject |  | 15 Oct | 21 Oct | 7 | Done | [80 empty] | Task |  | 2026-10-15 | 2026-10-21
Pause after a rejected rep with fix text; walk-away ends the session |  | 20 Oct | 22 Oct | 3 | Done | [80 empty] | Task |  | 2026-10-20 | 2026-10-22
Wrist-height tempo and lowering-speed check |  | 26 Oct | 27 Oct | 2 | Done | [80 empty] | Task |  | 2026-10-26 | 2026-10-27
7. Test OpenCV/MediaPipe detection under varying lighting conditions | W7 | 20 Oct | 11 Nov | 23 | In progress | [80 empty] | Heading |  | 2026-10-20 | 2026-11-11
Record test clips for repeatable testing (tools/record_clips.py) |  | 20 Oct | 27 Oct | 8 | Done | [80 empty] | Task |  | 2026-10-20 | 2026-10-27
Lighting tests (bright, dim, backlit) and record results |  | 9 Nov | 11 Nov | 3 | Not started | [80 empty] | Task |  | 2026-11-09 | 2026-11-11
8. Test detection under varying distances/backgrounds; tune thresholds for stability | W8 | 8 Oct | 12 Nov | 36 | In progress | [80 empty] | Heading |  | 2026-10-08 | 2026-11-12
Tune angle, visibility and confidence thresholds |  | 8 Oct | 27 Oct | 20 | Done | [80 empty] | Task |  | 2026-10-08 | 2026-10-27
Distance and background tests and record results |  | 10 Nov | 12 Nov | 3 | Not started | [80 empty] | Task |  | 2026-11-10 | 2026-11-12
Frame-rate check on the Pi 5 (CNN every 3rd frame, camera watchdog) |  | 27 Oct | 6 Nov | 11 | In progress | [80 empty] | Task |  | 2026-10-27 | 2026-11-06
9. Develop supporting modules: display overlay, GPIO feedback, calorie tracking, session logging (CSV) | W9 | 21 Sep | 6 Nov | 47 | In progress | [80 empty] | Heading |  | 2026-09-21 | 2026-11-06
On-screen overlay, debug view, start-up demo and full screen |  | 21 Sep | 27 Oct | 37 | Done | [80 empty] | Task |  | 2026-09-21 | 2026-10-27
Calorie estimate (MET 3.5, 2024 Compendium) and session summary |  | 15 Oct | 22 Oct | 8 | Done | [80 empty] | Task |  | 2026-10-15 | 2026-10-22
CSV session log and Flask phone app: accounts, QR login, history |  | 15 Oct | 27 Oct | 13 | Done | [80 empty] | Task |  | 2026-10-15 | 2026-10-27
Goal for the next session from guidelines (ACSM 2009, WHO 2020) |  | 19 Oct | 22 Oct | 4 | Done | [80 empty] | Task |  | 2026-10-19 | 2026-10-22
GPIO feedback module with the LEDs and buzzer (moved) |  | 4 Nov | 6 Nov | 3 | Not started | [80 empty] | Task |  | 2026-11-04 | 2026-11-06
10. Design and 3D print the Raspberry Pi/display/LED enclosure (Bambu Lab X1 Carbon, PLA) | W10 | 2 Oct | 13 Nov | 43 | In progress | [80 empty] | Heading |  | 2026-10-02 | 2026-11-13
Enclosure CAD in Fusion 360 (tray, port openings, hinged lid) |  | 2 Oct | 6 Nov | 36 | In progress | [80 empty] | Task |  | 2026-10-02 | 2026-11-06
Polished design (supervisor): rounded shape, camera mounts, cable routing, logo |  | 2 Nov | 8 Nov | 7 | Not started | [80 empty] | Task |  | 2026-11-02 | 2026-11-08
Test-print one section and check the fit |  | 7 Nov | 9 Nov | 3 | Not started | [80 empty] | Task |  | 2026-11-07 | 2026-11-09
Print the full enclosure and finish it (sanding, two colours) |  | 10 Nov | 13 Nov | 4 | Not started | [80 empty] | Task |  | 2026-11-10 | 2026-11-13
11. Assemble hardware into the enclosure; integrate pipeline on Raspberry Pi 5 (camera, GPIO, Flask endpoint) | W11 | 21 Oct | 15 Nov | 26 | In progress | [80 empty] | Heading |  | 2026-10-21 | 2026-11-15
Integrate the software on the Pi (both cameras, Flask app) |  | 21 Oct | 27 Oct | 7 | Done | [80 empty] | Task |  | 2026-10-21 | 2026-10-27
Mount the Pi, cameras, LEDs and buzzer in the enclosure |  | 13 Nov | 15 Nov | 3 | Not started | [80 empty] | Task |  | 2026-11-13 | 2026-11-15
12. End-to-end system testing and accuracy/reliability evaluation; write and finalise report; submission buffer | W12 | 27 Oct | 25 Nov | 30 | In progress | [80 empty] | Heading |  | 2026-10-27 | 2026-11-25
Repeated test sessions: automated vs manually counted reps |  | 9 Nov | 14 Nov | 6 | Not started | [80 empty] | Task |  | 2026-11-09 | 2026-11-14
Fix issues found; software and hardware complete (code freeze) |  | 12 Nov | 15 Nov | 4 | Not started | [80 empty] | Task |  | 2026-11-12 | 2026-11-15
Demo videos on Google Drive (bicep curl, exit session) |  | 27 Oct | 28 Oct | 2 | Done | [80 empty] | Task |  | 2026-10-27 | 2026-10-28
Final demo video and results for the report |  | 14 Nov | 16 Nov | 3 | Not started | [80 empty] | Task |  | 2026-11-14 | 2026-11-16
Report: introduction, literature review, methodology |  | 2 Nov | 13 Nov | 12 | Not started | [80 empty] | Task |  | 2026-11-02 | 2026-11-13
Report: results, discussion, conclusions |  | 14 Nov | 20 Nov | 7 | Not started | [80 empty] | Task |  | 2026-11-14 | 2026-11-20
Report: project management and quality management review |  | 17 Nov | 21 Nov | 5 | Not started | [80 empty] | Task |  | 2026-11-17 | 2026-11-21
Proofread, similarity check (<20%), submit (buffer) |  | 22 Nov | 25 Nov | 4 | Not started | [80 empty] | Task |  | 2026-11-22 | 2026-11-25
13. Prepare VIVA slides and rehearse the demo (added) | - | 26 Nov | 1 Dec | 6 | Not started | [80 empty] | Heading |  | 2026-11-26 | 2026-12-01
Prepare the 8 VIVA slides |  | 26 Nov | 30 Nov | 5 | Not started | [80 empty] | Task |  | 2026-11-26 | 2026-11-30
Rehearse the presentation and live demo |  | 28 Nov | 1 Dec | 4 | Not started | [80 empty] | Task |  | 2026-11-28 | 2026-12-01
14. Two-camera approach (added) | - | 12 Oct | 28 Oct | 17 | Done | [80 empty] | Heading |  | 2026-10-12 | 2026-10-28
AI Camera at the front + USB webcam at the side; fist/palm from both views |  | 12 Oct | 21 Oct | 10 | Done | [80 empty] | Task |  | 2026-10-12 | 2026-10-21
Find the cameras automatically (front / side) |  | 21 Oct | 22 Oct | 2 | Done | [80 empty] | Task |  | 2026-10-21 | 2026-10-22
Review at Session 3: fist direction left as a limitation |  | 28 Oct | 28 Oct | 1 | Done | [80 empty] | Task |  | 2026-10-28 | 2026-10-28
15. Weight-in-hand CNN (added) | - | 27 Oct | 10 Nov | 15 | In progress | [80 empty] | Heading |  | 2026-10-27 | 2026-11-10
Collect labelled hand crops (about 9,500, front + side) |  | 27 Oct | 27 Oct | 1 | Done | [80 empty] | Task |  | 2026-10-27 | 2026-10-27
Fine-tune MobileNetV3-Small, export ONNX, run with OpenCV (98.5 %) |  | 27 Oct | 27 Oct | 1 | Done | [80 empty] | Task |  | 2026-10-27 | 2026-10-27
Feasibility test: AI Camera on-chip object detector |  | 31 Oct | 31 Oct | 1 | Done | [80 empty] | Task |  | 2026-10-31 | 2026-10-31
Round 3 data: 3D-printed dumbbell, other objects and people |  | 3 Nov | 10 Nov | 8 | Not started | [80 empty] | Task |  | 2026-11-03 | 2026-11-10
16. Extra features suggested by the supervisor at Session 3 (added) | - | 2 Nov | 13 Nov | 12 | Not started | [80 empty] | Heading |  | 2026-11-02 | 2026-11-13
Personalised session report (PDF from the phone app) |  | 2 Nov | 9 Nov | 8 | Not started | [80 empty] | Task |  | 2026-11-02 | 2026-11-09
Speech-to-text voice commands (start, stop, summary) - offline |  | 5 Nov | 13 Nov | 9 | Not started | [80 empty] | Task |  | 2026-11-05 | 2026-11-13
Polished 3D chassis - see task 10 |  | 2 Nov | 13 Nov | 12 | Not started | [80 empty] | Task |  | 2026-11-02 | 2026-11-13
17. Battery power - if time allows (added) | - | 10 Nov | 14 Nov | 5 | Not started | [80 empty] | Heading |  | 2026-11-10 | 2026-11-14
Battery path (fuse, SB560 diode, HW-688) and load test (optional) |  | 10 Nov | 14 Nov | 5 | Not started | [80 empty] | Task | Yes | 2026-11-10 | 2026-11-14
Milestones | [85 empty] | Heading2
◆ Session 1 - Project review 1 (Logbook 5) |  | 23 Sep | 23 Sep | 0 | Done | [80 empty] | Milestone |  | 2026-09-23 | 2026-09-23 | bar: Week 2 23 W
◆ Session 2 - Project review 2 (Logbook 6) |  | 7 Oct | 7 Oct | 0 | Done | [80 empty] | Milestone |  | 2026-10-07 | 2026-10-07 | bar: Week 4 7 W
◆ Software target - reps counted reliably on the Pi |  | 22 Oct | 22 Oct | 0 | Done | [80 empty] | Milestone |  | 2026-10-22 | 2026-10-22 | bar: Week 6 22 T
◆ Session 3 - Project review 3 (Logbook 7) |  | 28 Oct | 28 Oct | 0 | Done | [80 empty] | Milestone |  | 2026-10-28 | 2026-10-28 | bar: Week 7 28 W
◆ Software and hardware complete (code freeze) |  | 15 Nov | 15 Nov | 0 | Not started | [80 empty] | Milestone |  | 2026-11-15 | 2026-11-15 | bar: Week 9 15 S
◆ Session 4 - Project review 4 (Logbook 8) |  | 18 Nov | 18 Nov | 0 | Not started | [80 empty] | Milestone |  | 2026-11-18 | 2026-11-18 | bar: Week 10 18 W
◆ Final project report submission |  | 25 Nov | 25 Nov | 0 | Not started | [80 empty] | Milestone |  | 2026-11-25 | 2026-11-25 | bar: Week 11 25 W
◆ VIVA slides submission |  | 30 Nov | 30 Nov | 0 | Not started | [80 empty] | Milestone |  | 2026-11-30 | 2026-11-30 | bar: Week 12 30 M
◆ Project defence (VIVA) and demo |  | 2 Dec | 2 Dec | 0 | Not started | [80 empty] | Milestone |  | 2026-12-02 | 2026-12-02 | bar: Week 12 2 W
Legend
Heading (outline task) - span of its subtasks
Done
In progress
Planned
Optional / still in development
Milestone
Weekend
Formulas:
Start date = MIN([Start date, row below]:CL13)
Start date = IFERROR(IF(TRIM([Start])="","",IF(ISNUMBER([Start]),[Start],DATE(2026,MATCH(LEFT(MID(TRIM([Start]),FIND(" ",TRIM([Start]))+1,9),3),Lists!$A1:A12,0),VALUE(LEFT(TRIM([Start]),FIND(" ",TRIM([Start]))-1))))),"")
End date = MAX([End date, row below]:CM13)
End date = IFERROR(IF(TRIM([End])="","",IF(ISNUMBER([End]),[End],DATE(2026,MATCH(LEFT(MID(TRIM([End]),FIND(" ",TRIM([End]))+1,9),3),Lists!$A1:A12,0),VALUE(LEFT(TRIM([End]),FIND(" ",TRIM([End]))-1))))),"")

## Lists (hidden)
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec

## Outline vs Actual
Comparison with the Project Outline Gantt chart (Appendix A)
Term week 1 = 14-20 Sep 2026, so outline week Wn = the n-th week from 14 Sep.
Outline task | Outline week (dates) | Updated span | Status (31 Oct) | Change and reason
Set up Python 3.11 virtual environment (Raspberry Pi OS + laptop) | W1 (14 Sep - 20 Sep) | 14 Sep - 02 Oct | Done | Took longer: Raspberry Pi OS Trixie ships Python 3.13, which MediaPipe does not support, so a Python 3.12 environment was made with uv.
Install and configure OpenCV | W2 (21 Sep - 27 Sep) | 16 Sep - 02 Oct | Done | Laptop done in W1; the Pi part was done together with task 1 in W3.
Install and configure MediaPipe; test camera feed and GPIO wiring for LED/buzzer | W3 (28 Sep - 04 Oct) | 17 Sep - 04 Nov | In progress | MediaPipe and camera done (AI Camera needed its firmware). GPIO wiring moved to early November to keep the focus on the software (critical path).
Develop MediaPipe Pose landmark extraction (shoulder, elbow, wrist, hip coordinates) | W4 (05 Oct - 11 Oct) | 19 Sep - 07 Oct | Done | Done early on the laptop (W1-W2); 3D landmarks added in W4.
Implement joint-angle calculation functions (elbow, torso, wrist angles) | W5 (12 Oct - 18 Oct) | 05 Oct - 08 Oct | Done | Done in W4; wrist angle from the hand knuckles; hip angle replaced by an upper-arm drift check because the hips are often out of view.
Build the bicep curl rep-counting state machine with form-validation checks | W6 (19 Oct - 25 Oct) | 21 Sep - 27 Oct | Done | Started early on the laptop (W2); live counting on the Pi took until 22 Oct. Fist direction could not be judged reliably from one camera; agreed with the supervisor to leave it as a limitation (advice only).
Test OpenCV/MediaPipe detection under varying lighting conditions | W7 (26 Oct - 01 Nov) | 20 Oct - 11 Nov | In progress | Test clips recorded in W6 so every change is tested on the same video; the formal lighting tests are run in W9 with the finished system.
Test detection under varying distances/backgrounds; tune thresholds for stability | W8 (02 Nov - 08 Nov) | 08 Oct - 12 Nov | In progress | Threshold tuning started early (W4) because counting did not work on the Pi; distance/background tests in W9.
Develop supporting modules: display overlay, GPIO feedback, calorie tracking, session logging (CSV) | W9 (09 Nov - 15 Nov) | 21 Sep - 06 Nov | In progress | Grew in scope: the CSV log became a Flask phone app with accounts, QR login, session history, calorie chart and a goal for the next session (W5-W7). GPIO feedback moved to W8.
Design and 3D print the Raspberry Pi/display/LED enclosure (Bambu Lab X1 Carbon, PLA) | W10 (16 Nov - 22 Nov) | 02 Oct - 13 Nov | In progress | CAD started early but paused while the software was fixed; the supervisor asked for a polished chassis, so the redesign and printing are W8-W9.
Assemble hardware into the enclosure; integrate pipeline on Raspberry Pi 5 (camera, GPIO, Flask endpoint) | W11 (23 Nov - 29 Nov) | 21 Oct - 15 Nov | In progress | Software integration on the Pi finished in W6-W7 (both cameras, phone app); mounting in the enclosure in W9.
End-to-end system testing and accuracy/reliability evaluation; write and finalise report; submission buffer | W12 (30 Nov - 06 Dec) | 27 Oct - 25 Nov | In progress | Demo videos already recorded (W7). Report writing starts in W8 so it is not left to the end; code freeze 15 Nov, report due 25 Nov.
Two-camera approach (added) | - | 12 Oct - 28 Oct | Done | Added to judge the fist and palm from the side; reviewed at Session 3.
Weight-in-hand CNN (added) | - | 27 Oct - 10 Nov | In progress | Added to check that a weight is held; 98.5 % on a new session; more data with a dumbbell next.
Supervisor's extra features (added) | - | 02 Nov - 13 Nov | Not started | Personalised report, speech-to-text and a polished chassis, suggested at Session 3.
VIVA slides and rehearsal (added) | - | 26 Nov - 01 Dec | Not started | Not in the outline; slides due 30 Nov, VIVA 2 Dec.